## Intro
4th Year Software Test Plan
Project Name | Login Console
Project Manager | Naomi Hurley
Prepared by | Naomi Hurley and the 4th year Computing students
Tech Lead | To be confirmed
Date
Revision History
Revision | Author | Comment
1 | Naomi Hurley | Initial Draft

## Product No 1 or Sprint No 1
Darren Regan, G00326934, Group C |  | Purpose: | This set of tests is intended to check the main functionality of my application
Testing and Test Plan for myAPP Testing Must include Andriod Testing as well and Desktop |  |  |  | Devices Tested With Laptop -Windows 10 Home Edition Version 10.0.17134 Build 17134 Desktop -Windows 10 Pro Edition Lastest Version Andriod Kitkat - Version 4.4.4 Andriod_Accelerated_x86_Orea (Andriod 8.1 - API 27) Andriod Emulator from Visual Studio 2017 Community Edition Browsers Tested Google Chrome Edge Firefox
Enviroment | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail | Bug # | Comments
Desktop Windows 10 Home + Pro | 1 | TC.001 | Launch Application Desktop | GUI | 1. Launch App 2. Retrieve first Tabbed Page of App | Check if tabs show up on top of screen sorting from left to right | Multiple tabs should display on top of screen and sorted from left to right | Multiple Tabs do display and are sorted from left to right | Pass
Desktop Windows 10 Home + Pro | 1 | TC.002 | Launch Application Desktop | GUI | 1. Launch App 2. Exit Application before loads app | Check if exiting app prematurely will cause unexcepted errors/issues | No Errors / Performance issues from exiting | Small delay in closing application/Sometimes Hangs for 1-10seconds | Fail | Defect No 12345 Priority-5 Severity-Low | Low Priority - Issue doesn't occur very often. To be assigned
Desktop Windows 10 Home + Pro | 1 | TC.003 | Test Navigation Bar | GUI | 1. Launch App 2. Click each tab on Nav Bar | Check if clicking each option on NavBar will enter a new scene | Clicking a Option from the NavBar will enter the scene correctly | Options on Navbar do enter the correct Scenes | Pass
Andriod | 1 | TC.004 | Launch Application Andriod | GUI | 1. Launch Andriod Emulator in VS 2017 2. Waiting for Emulator to load completely 3. Receive first Tabbed Page of App | Check if tabs show up on an andriod phone | Multiple tabs should display on top of screen and sorted from left to right | Multiple Tabs do display and are sorted from left to right | Pass
Andriod | 1 | TC.005 | Launch Application Andriod | GUI | 1. Launch App 2. Press HomeButton/Back Button on Emulator 3. Press Overview or Ctrl + O 4. Click back to myApp | Check for any issues on phones if user were to press back/homepage/close app | User should be able to seemlessly come back to application if they use back/home button | Can use back button and then overview to click back into myApp | Pass
Andriod | 1 | TC.006 | Test Navigation Bar | GUI | 1. Launch App 2. Wait for Emulator to load 3. Once in App Click all of the options in the NavBar to display scenes | Check if mobile can see NavBar & options and are able to click them to display scenes | Mobile should display Navbar and Options in a compact version of app | Mobile shows NavBar and options well. They have to be changed abit so more info can be seen | Pass |  | Make adjustments to Navbar to make it smaller by like 20% so user can see more information
Andriod | 1 | TC.007 | Login credentials | GUI
| 1 | TC.008 | Password reset | GUI
| 1 | TC.009 | Password reset | GUI
| 1 | TC.010 | Password reset | GUI
| 1 | TC.011 | Email confirmation | GUI
| 1 | TC.012 | Email confirmation | GUI
| 1 | TC.013 | Email confirmation | GUI
| 1 | TC.014 | Email confirmation | GUI
| 1 | TC.015 | Social login Facebook | GUI
| 1 | TC.016 | Social login Twiter | GUI
| 1 | TC.017 | Social login Google+ | GUI

## Product No 2 or Sprint No 2
|  | Purpose: | This set of tests is intended to check main functionality developed
Test Run Title e.g. Login validation |  |  |  | Microsoft Internet Explorer 9 Windows 7 Microsoft Internet Explorer 10 Windows 7 Micresoft Internet Explorer 11 Windows 7 Microsoft Internet Explorer 8 Windows XP Microsoft Internet Explorer 7 Windows XP Firefox latest version Apple Safari Windows XP Apple Safari Google Chrome Windows XP Opera Windows XP
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Results Pass/Fail | Bug # | Comments

## Test Progress
Tabs | Developped by | No of test cases | Tester | No of days | Browsers | Test cases passed | Test cases failed | To be done | Percentage done
Sprint No
Test Run description | Team A | 18 |  |  | All | 0 | 0 | 18 | 0%
Test Run description | Team B | 8 |  |  | N/A | 0 | 0 | 8 | 0%
Test Run description | Team C | 19 |  |  | All | 0 | 0 | 19 | 0%
Test Run description | Team D | 20 |  |  | All | 0 | 0 | 20 | 0%
Test Run description | Team C | 42 |  |  | All | 0 | 0 | 42 | 0%
Total |  | 107 |  |  |  |  | 0 | 0 | 0%